REPORT ON LIGHTUP YOUNG HERITAGE AMBASSADORS

PROJECT

LINKS TO IMPORTANT PROJECT INFORMATION

Link to Haringey Independent Newspaper’s Press Release

http://www.haringeyindependent.co.uk/news/10399966.Foundation_secures___32_500_to_educate_young_people_about_local_heritage/

DOCUMENTARY FOR THE 2 BOROUGHS

Documentary of Haringey High Road

http://www.youtube.com/watch?v=Q-I1BYUnd9c

Documentary of Croydon High Street

http://www.youtube.com/watch?v=xE1uJx3oFwU

NEWSPAPER PUBLICATION ON AWARD CEREMONY AND MAGAZINE LAUNCH

http://www.haringeyindependent.co.uk/news/10845761.Teenagers_launch_heritage_magazine/

AWARD CEREMONY AND MAGAZINE LAUNCH (On YouTube)

Croydon link: http://www.youtube.com/watch?v=GKddGpsMGbQ

Haringey Link: http://www.youtube.com/watch?v=2X3DTAnl47w&feature=youtu.be

# Text boxes

LIGHTUP FOUNDATION

Location: Croydon & Haringey Borough

November 2012 - January 2014

INTRODUCTION

Lightup Foundation is a charity presently operating in Croydon and other boroughs within London. The Lightup Foundation works to improve youth and community development.

After the incident of the London riots, we decided to speak to young people in the community to know what they felt caused the riots and the reason why any one will decide to destroy the assets in their community in a protest. We had an inter-school debate on the 4th of October 2011, 150 young people as well as a BBC researcher and other relevant organisations and persons were present. Young people talked about the riot and how we could prevent a future repeat of such incident.

At the end of the debate most young people agreed that young people lacked the sense and pride of ownership of their community and that was why it was easy to cause damage to show their anger towards the government for not listening to them.

After this debate we embarked on various youth consultations, talks and road shows within Tottenham and Croydon and it became more glaring that a lot of young people were disconnected from their local communities. Majority of the young people we spoke to were not interested in what was happening in their community never mind wanting to be part of the local activities.

During one of our community tours with young people in Croydon, a question was put forward:

“Why did the young people who burnt down buildings during the riot not burn down their own houses to show the government that they are angry with them”?

From all the answers we got from young people majority felt that most young people felt that their home was theirs, they had a stake in it and it was not right to destroy it.

From these answers we concluded that most young people are not aware that their community is theirs, and they have a stake in it and the Community is their heritage which is of inestimable value. As the saying goes “If the value of a thing is not known, then its abuse becomes inevitable”.

As a result, we decided to embark on a Heritage project which would help young people to get connected to the history of their community; create an awareness of their communities; celebrate their communities; encourage them to develop the pride of ownership of their communities and learn to protect it.

The Lightup Young Heritage Ambassadors Project is a new and exciting concept, with the aim of re-connecting young people to their community by creating an awareness of their local heritage. Lightup Foundation a registered charity strongly believes that this is a way forward in addressing the occurrence of the violence, opportunistic looting, vandalism and arson on historical buildings during the London riots back in August 2011.

HOW THE ROJECT WAS IDENTIFIED

Lightup acts as a resource for young people by providing support, advice, assistance and organising educational programmes. Lightup helps young people develop their skills and capacities to help them participate positively in society as independent, mature and responsible individuals.

OUR PROFILE

THE PROJECT

SUMMARY OF THE YOUNG HERITAGE AMBASSADORS PROJECT

TARGETED AREAS

PROJECT AIMS AND OBJECTIVES

| 1. | To make young people aware of their local heritage and communities and help these young people to celebrate their own heritage and communities. |
| --- | --- |
| 2. | To encourage young people to develop the pride in and ownership of their local heritage and communities and learn to protect it. |
| 3. | To equip young people with the required skills in recording Heritage information, research work and help to build their confidence in making presentations and demonstrating leadership among the youth in their communities. |

All activities within this project commenced in November 2012 and ended in January 2014.

PROJECT FUNDING

At the end of our needs assessment exercise we applied for grant from the Young Roots Heritage Lottery Funds. In November 2012, we were given a grant of £32,500 by the HLF team.

PROJECT DURATION

| 1. | Haringey Libraries |
| --- | --- |
| 2. | Bruce Castle Museum |
| 3. | St Mary’s Catholic High School, Croydon |
| 4. | Reeve’s Furniture Business Croydon |
| 5. | Croydon Local Studies Library and Archives Service |
| 6. | Royal Institute of British Architect (RIBA) |
| 7. | John Loughborough School Haringey |

PROJECT PARTNERS & SUPPORTERS

| A. | The Borough of Haringey (Tottenham) |
| --- | --- |
| B. | The Borough of Croydon (Central Croydon) |

| 6. | Exhibition and briefing of the research findings in selected schools and youth clubs within Croydon and Haringey (and also exhibiting with our heritage partners). |
| --- | --- |
| 7. | The Preparation of a Croydon and Haringey Young Heritage Magazine, which was, distributed in schools, libraries and youth organisations within the two boroughs. |

| 4. | An exchange tour between the young people in Croydon and Haringey (Tottenham) borough. (In a bid to exchange research information/findings). |
| --- | --- |
| 5. | Project documentary preparation |

| 1. | A NOW and THEN intensive research of the Tottenham and Croydon High streets |
| --- | --- |
| 2. | Research using historical archives and local resources to investigate some of the heritage buildings burnt during the riot |
| 3. | Tours of the High streets and the burnt buildings (with guidance from heritage experts and local traders/ people). |

THE FOLLOWING ARE THE SUMMARY OF THE VARIOUS ACTIVITIES THAT WERE CARRIED OUT UNDER THE HERITAGE PROJECT.

BRIEF OF WHAT HAPPENED ON THE PROJECT

We set out to work with 10 young people from Haringey and another 10 from Croydon, a lot of young people were interested in participating on this project as a result we had to accommodate more young people during the admission process.

We selected 15 young people (project direct beneficiaries) and 11 young volunteers from Croydon and another 15 (project direct beneficiaries) and 5 young volunteers from Haringey. Young people were exposed to the NOW and THEN research of their High street, at some point during the project, young people had exchange tours within Croydon and Haringey to explore the other group’s findings. Subsequently, the research information was exhibited in schools, youth clubs, social networking sites and other public places in a bid to give back the young people’s research within the 2 boroughs.

The details of the research were documented in the form of a First Youth Heritage Magazine for Croydon and Haringey and in Documentary format.

To ensure the success of this project, Lightup worked in partnership with the Royal Institute of British Architects (RIBA), Haringey Libraries and Bruce Castle Museum (which is under the Haringey Culture, Libraries and Learning), St Mary’s Catholic High School, John Loughborough School and Croydon Local Studies Library and Archives Service on the project.

London Academy of Media Film and Television provided project trainings. Reeve’s Furniture Business Croydon and many other local businesses offered their full support and willingness in assisting the project.

The board of directors nominated the Project Co-ordinator due to her experience, selflessness, service and the overwhelming success working on former Lightup Youth and Community Projects.

At the start of the project staff recruitment was a bit of a challenge, we had to use part of our contingencies to employ the service of a qualified and experienced youth worker to set up the project.

We visited the partner schools to make presentations to the students and a number of young people were interested in getting involved in the project. It was quite challenging to turn down the interested young people and in a bid to motivate young people we had to admit more than 10 young people for each of the boroughs.

Project application was open to any young person between the ages of 11 -25 who lived, attended school or spent most of their time in Croydon or Haringey.

PROJECT EXECUTION

ELIGIBILITY FOR THE LIGHTUP YOUNG HERITAGE

AMBASSASORS PROJECT

| 1. | Documentary Preparation Training |
| --- | --- |
| 2. | Leadership and Confidence Boosting training |
| 3. | Research with the Royal Institute of British Architects |
| 4. | Croydon Now and Then Library Research of the Croydon High street and Haringey Now and Then Library Research of the Tottenham High Road |
| 5. | Tour of the High streets |
| 6. | Exchange tour “Croydon Group visit Haringey” (Tottenham) and |
| 7. | Exchange tour “Haringey Group visit Croydon” (Croydon High Street) |

PROJECT TRAINING AND ACTIVITIES

Young People on this Project were exposed to the Following Trainings and Activities:

INFORMATION ON VARIOUS ACTIVITIES CARRIED OUT UNDER THE PROJECT

| Group | Date | Activity | Venue | Outcome |
| --- | --- | --- | --- | --- |
| Haringey Group | 29-05-2013 | Group A Documentary Preparation Training | London Academy of Media Film & TV 1 Lancing St London Borough of Camden NW1 1NA | A. 80% of the Participants said their expectations were met. B. Participants learnt how to make a documentary film, record buildings, and interview local people C. All trained participants received a diploma certificate in Documentary Awareness |
|  | 29-06-2013 | Group B Documentary Preparation Training | London Academy of Media Film & TV 1 Lancing St London Borough of Camden, NW1 1NA | 70% of the Participants said their expectations were met. B. Participants learnt how to make a documentary film, record buildings, and interview local people C. All trained participants received a diploma certificate in Documentary Awareness |
| Croydon Group | 12-04-2013 | Documentary Preparation Training | London Academy of Media Film & TV 1 Lancing St London Borough of Camden, NW1 1NA | 85% of the Participants said their expectations were met. B. Participants learnt how to make a documentary film, record buildings, and interview local people C. All trained participants received a diploma certificate in Documentary Awareness |

DOCUMENTARY PREPARATION TRAINING

| Group | Date | Activity | Venue | Outcome |
| --- | --- | --- | --- | --- |
| Haringey Group | 31-05-2013 | Group A - Leadership training and - Confidence Boosting training tailored to the project. | Holy Trinity, Tottenham Philip Lane, Tottenham, London, N15 4GZ | A. 82% of the Participants said their expectations were met. B. Participants were equipped with the leadership skills required to run a successful project. C. Participants were empowered with leadership skills which made them to lead and got more actively involved in the project. Participants took charge of project activities e.g. planning and running of the Project. D. All the trained participants received training Certificates on Leadership and Confidence Boosting. |
|  | 12-07-2013 | Group B - Leadership training and - Confidence Boosting training tailored to the project | The John Loughborough School. Holcombe Road, Tottenham, London N17 9AD | A. 75% of the Participants said their expectations were met. (B, C and D Outcomes above also apply here). |
| Croydon Group | 16-04-2013 | - Leadership training and - Confidence Boosting training tailored to the project. | St Mary's Catholic High School Woburn Road Croydon CR9 2EE | 88% of the Participants said their expectations were met. (B, C and D Outcomes above also apply here). |

LEADERSHIP AND CONFIDENCE BOOSTING TRAINING

RESEARCH WITH THE ROYAL INSTITUTE OF BRITISH ARCHITECTS TRAINING

| Group | Date | Activity | Venue | Outcome |
| --- | --- | --- | --- | --- |
| Haringey Group | 02-07-2013 | Research with the Royal Institute of British Architects | The Headquarters of The Royal Institute of British Architects British Architectural Library 66 Portland Place London W1B 1AD | A. 86% of the Participants said their expectations were met. B. Participants understanding of and appreciation for the architecture in their own communities was enhanced. C. The exercise enriched the research work by the young people and gave them the opportunity to explore material from the RIBA’s world-class collections. They developed critical skills in looking at, forming opinions of and speaking about architecture and the built environment that surrounds them. D. Project participants received “Research skills and architecture awareness workshop certificate” from the Royal Institute of British Architecture (RIBA) to enhance their profile |
| Croydon Group | 27-04-2013 | Research with the Royal Institute of British Architects | The Headquarters of The Royal Institute of British Architects British Architectural Library 66 Portland Place London W1B 1AD | A. 82% of the Participants said their expectations were met. (Outcomes B.C and D above also apply here). |

| Group | Date | Activity | Venue | Outcome |
| --- | --- | --- | --- | --- |
| Haringey Group | 01-06-2013 | Group A Haringey Now and Then Library Research of the Tottenham High Road | Bruce Castle Museum Haringey Culture, Libraries and Learning Lordship Lane, London N17 8NU | A.78% of the participants said their expectations were met B. Participants were exposed to the modern day high street scene of today with the same areas depicted in the Victorian and Edwardian periods. They also looked at changes during the 20th century at the time of Second World War and then the 1950s in Tottenham high road. C. Participants gathered research information on the extraordinary built heritage of the historical corridor of Tottenham High Road. D. Participants acquired experience of their own interpretations and value of their historical built environment. E. Participants also looked at some of the affected buildings during the 2011 London riot. |
|  | 26-06-2013 | Group B Now and Then Library Research of the Tottenham High Road | Bruce Castle Museum Haringey Culture, Libraries and Learning Lordship Lane, London N17 8NU | A.82% of the participants said their expectations were met (Outcomes B.C, D and E above applies here as well). |
| Croydon Group | 30-04-2013 | First Now and Then Library Research of the Croydon High street | Croydon Local Studies Library and Archives Service, Central Library Katharine Street Croydon CR9 1ET | A.88% of the participants said their expectations were met B. Participants acquired skills in researching information on the Now and Then comparison of the modern day environment with the great rebuilding of Central Croydon High street in the 1890s. Comparison was also drawn with other significant period of urban change in the World War II and post war periods C. Participants also carried out research on the East Croydon station and the Croydon Airport E. Participants also looked at some of the affected buildings during the 2011 London riot. |
|  | 1-05-2013 | Second Now and Then Library Research of the Croydon High street | Croydon Local Studies Library and Archives Service Central Library Katharine Street Croydon CR9 1ET | A.85% of the participants said their expectations were met. Continuation of research work on the topics mentioned in outcomes B, C and D above. |

NOW AND THEN LIBRARY RESEARCH TRAINING

TOUR OF THE HIGH STREET

| Group | Date | Activity | Venue | Outcome |
| --- | --- | --- | --- | --- |
| Haringey Group | 31- 05-2013 | Group A Tour of the Tottenham High Road | Tottenham High Road | A. 90% felt that their expectations were met. They had real life experience during the tour of the high street; it was very fascinating to most of the project participants. B. Participants visited the buildings affected during the 2011 London riots, It helped them to know more about their community heritage and they really appreciated this opportunity. |
|  | 26-06-2013 | Group B Tour of the Tottenham High Road | Tottenham High Road | A. Participants found this aspect of the project really interesting; they also had the opportunity to meet with local people and traders on the high road. B. Participants visited the buildings affected during the 2011 London riots; They really appreciated the visit and got to know how valuable the lost historic buildings were. |
| Croydon Group | 04-05-2013 | Croydon Group tour of the Croydon High street | Croydon High street | 95% of the participants benefitted greatly from the tour B. Participants visited the buildings affected during the 2011 London riot; They appreciated the visit and got to know how valuable the lost historic buildings were. |

EXCHANGE TOUR BETWEEN HARINGEY GROUP AND CROYDON GROUP

| Group | Date | Activity | Venue | Outcome |
| --- | --- | --- | --- | --- |
| Haringey Group | 13-07-2013 | Haringey Group visit Croydon | Croydon High street and St Mary's Catholic High School Woburn Road, Croydon CR9 2EE | A. New opportunities were created for participants to learn about their community heritage and also the Croydon heritage; B. It was an Opportunity for participants from Haringey to exchange their research information with participants from Croydon. C. Young people had the opportunity to network and share project experience with others |
| Croydon Group | 07-07-2013 | Croydon Group visit Haringey group | - Tottenham High street and - Bruce Castle Museum Haringey Culture, Libraries and Learning Lordship Lane, London N17 8NU | A. New opportunities was created for participants to learn about their community heritage and also the Haringey (Tottenham) heritage; B. It was an Opportunity for participants from Croydon to exchange their research information with participants from Haringey. C. Young people had the opportunity to network and share project experience with others. |

PROJECT PARTICIPANTS

HARINGAY VOLUNTEERS

CROYDON GROUP

HARINGAY VOLUNTEERS

HARINGAY GROUP

- Hishan

- Noel

- Khasmina

- Jael

- Rachael Adechi

- Norbort  Wojuak

- Jean Piette Ivanov

- Davina Appiagyei

- Lisa Stewart

- Demir Kadir

- Melvina Eshon

- Thelma Gossel

- Ayse Demir

- Ganiyat Ogunsanya

- Chinaza  Okonkwo

- Abimbola Aderibigbe

- Jenelle Mantey

- Ricki Adechi

- Michelle Mauoungou

- Ekene Ikem

- Donia Chaouachi

- Nimra Chaudhary

- Malek Chaouachi

- Javelle Nelson

- Fatma Chaouachi

- Beatrice Saah

- Ngozi  Ikweke

- Augustin Muanda

- Sonia Woods

- Rebbeca Mc

- Jaqan

- Oliur Rahman

- Damla Yilmaz

- Kyasia Francis

- Rogerio

- Shyann Martin

- Semar Byrue

- Nathaniel Dabreo

- Jesse Landu

- Rishana Morris

- Micheal Roe

- Shawana Martin

- Jerome Manghton

- Jennifer. A.  Augustus

- Stefan Samu

- Kayley O’neill

.

GENDER BREAKDOWN

EQUAL OPPORTUNITY DATA OF PROJECT BENEFICIARIES

HARINGEY

CROYDON

AGE BREAK DOWN OF PROJECT BENEFICIARIES (%) ()

HARINGEY

CROYDON

ETHNIC BACKGROUND OF PROJECT BENEFICIARIES

HARINGEY

CROYDON

GIVING BACK THE PROJECT LOCALLY

At the end of this project we have produced 5,000 copies of Haringey Youth Heritage Magazines and another 5.000 of Croydon Youth Heritage Magazines.

We also produced 20 copies of the documentary research DVD of the Tottenham High road (Haringey) and 20 copies of the documentary research DVD of the Croydon High street.

Presently we have distributed the magazines to the places listed below in both HARINGEY and CROYDON

- All secondary schools (private, public and special schools)

  - Breakdown of Croydon Secondary Schools

    - 18 Public Secondary Schools

    - 6 Special Education Secondary Schools

    - 13 Private Secondary schools.

  - Breakdown of Haringey Secondary Schools

    - 11 Public Secondary Schools

    - 4 Special Education Secondary Schools

    - 4 Private Secondary schools.

- All libraries

  - Croydon Libraries

    - 13 Libraries including the central library

  - Haringey Libraries

    - 9 Libraries

- All Youth clubs

  - Haringey Youth Clubs

    - 3 youth clubs

  - Croydon Youth Clubs

    - 8 Youth clubs

- All councilors and selected community leaders in the 2 boroughs.

We had limited copies of the documentary DVDs (i.e. 20 copies/borough making a total of 40 DVDs) ) produced by young people therefore we have given these out to selected community leaders, schools and the young people involved in the project

Young project beneficiaries have being sharing their knowledge in Secondary schools and youth clubs within Haringey and Croydon borough.

GIVE BACK EXERCISE IN CROYDON:

Young beneficiaries in Croydon have been able to give back to approximately 1,050 young people in  schools and community groups, through their documentary DVDs and exhibition.

GIVE BACK EXERCISE IN HARINGEY:

In Haringey, young people have given back to approximately 400 young people in school and youth club via their documentary DVD and exhibition.

At the moment we have received several mails and interest to collaborate on this project in the future.

- In the future we will look to secure funds to employ a full time project coordinator to run this project, the delivery time and work on this project was under estimated.

- We will seek to get all partners more involved with project execution and planning.

- We will work towards securing a mini project office where this project will be run from.

WHAT WE PLAN TO DO BETTER IN THE FUTURE (LESSONS LEARNT)?

- 95% of the project participants were delighted to be involved in the project, this project has helped the direct beneficiaries to gain confidence in starting and completing a major task.

- Project participants have gained prominence in the community via this project and this has helped them to raise their future aspirations in life.

- At the end of this project young people received 3 major certificates and an Award of excellence plaque

  - A diploma certificate in Documentary Awareness from London Academy of Media Film & TV.

  - Leadership and Confidence Boosting from Lightup Foundation.

  - Research skills and architecture awareness workshop certificate from the Royal Institute of British Architecture (RIBA)

- The awareness on the community heritage has been mind blowing to majority of the young people and as a result of these new discoveries, project participants have become more confident and willing to share the knowledge of their community heritage with more people in the community.

- Croydon project participants have recently been invited to the Croydon Mayor’s parlour where they received badges from the mayor to encourage the good work the young people are involved with. Haringey Independence News paper has also published the Haringey young people’s achievement in their papers.

- 85% of older people who were invited to the young people’s Award ceremony were amazed by the research work and the history behind the community buildings they have indicated that this project should not be restricted to only young people.

- We have received overwhelming number of encouraging messages, mails, phone calls and interested organisations willing to partner with us to execute similar projects in the future.

HOW THE PROJECT IDEA HAS BENEFITED YOUNG PEOPLE

CROYDON GROUP

HARINGEY GROUP

SELECTED BENEFICIARY QUOTES

Stefan Samu:

“Very helpful and interesting source of information about our borough, the history of Tottenham high road and also important facts about Hotspur.”

Rogerio:

“I felt that this was well needed, especially on my second visit . I felt that I learnt a great deal and would recommend this to anybody.”

Damla Yilmaz:

“This project looks very interesting and helpful. Hopefully we will achieve and get a good experience.”

Nathaniel Dabreo:

“On this project, I have learnt a large amount of information about the Tottenham high road. I have had an insight of the early business of Tottenham. I have also taken the task of researching the high cross.”

Kyasia Francis Mc Donalds:

“I think the project went really well and I’ve learnt a lot and I’ve picked up a lot of information and I hope to see all these in our magazine.”

Shyann Martin:

“In my opinion, I believe the project is going very well and I shall continue to progress.”

Jenelle Mantey:

“It was really exciting and I got to learn a lot of things about Croydon.”

Fiona Owusu:

“This was a real eye opener, I have found out many things about my local area. I never knew before. An excellent experience.”

Beatrice Saah:

“This experience as been a real amazing roller coaster. I have done things and met people I didn’t dream of meeting. It has been wonderful. I love it here, it’s fantastic.”

Ayse Demir:

“My name is Ayse and I feel the project has helped me a lot in knowing the history of Croydon.”

Michelle Mavoungou:

“I‘ve really enjoyed doing the Ligtup Foundation project. It has allowed me to see Croydon in a different light and with more respect.”

Malek Chaouachi:

“This Lightup Foundation project is a massive experience to me. It has boosted up my confidence. I have enjoyed my time after school when we go out. It has been amazing.”

Jenelle Mantey:

“This Lightup Foundation project has been a life changing experience for me and I feel very honoured and proud to have been a part of such an amazing project. It helped me to know where I live (Croydon) more. I am very thankful.”

Donia Chaouachi:

“Lighup Foundation has changed the way I see things and it is a life changing experience for me being a part of this project. I have now understood more about my community thanks to Lightup Foundation. I respect it. “

LIGHTUP FOUNDATION